## Gantt Chart
CETM46 Data Science Product Development | [7 empty] | Smartsheet Tip ➜ | [7 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  |  | Ben Ho - Assignment 1 |  |  |  |  | COMPANY NAME | [8 empty] | University of Sunderland
PROJECT MANAGER |  |  | Ben Ho |  |  |  |  | DATE | [8 empty] | 2022-10-29
WBS NUMBER | TASK TITLE | DELIVERABLES | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | NOVEMBER | [29 empty] | DECEMBER
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 |  |  |  | WEEK 1 |  |  | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Planning
1.1 | Brainstorming of topics ideas | Initial Topics | Ben Ho | 2022-11-01 | 2022-11-05 | 4 | 0% | bar: WEEK 1 1 to WEEK 1 5
1.2 | Initial Research on topic ideas | List of Research Results | Ben Ho | 2022-11-06 | 2022-11-10 | 4 | 0% | bar: WEEK 2 6 to WEEK 2 10
1.3 | Conclude and decide on a topic | Identified Topic | Ben Ho | 2022-11-11 | 2022-11-13 | 2 | 0% | bar: WEEK 2 11 to WEEK 3 13
2 | Research
2.1 | Detail Research on the topic | List of Research Results | Ben Ho | 2022-11-14 | 2022-11-20 | 6 | 0% | bar: WEEK 3 14 to WEEK 4 20
2.2 | Consolidation of Reseach Results | Research Consolidated List | Ben Ho | 2022-11-21 | 2022-11-25 | 4 | 0% | bar: WEEK 4 21 to WEEK 4 25
2.3 | Define Project Direction | Project Direction Statement | Ben Ho | 2022-11-26 | 2022-11-27 | 1 | 0% | bar: WEEK 4 26 to WEEK 5 27
3 | Implementation
3.1 | Define Problem Statement | Problem Statement | Ben Ho | 2022-11-28 | 2022-11-30 | 2 | 0% | bar: WEEK 5 28 to WEEK 5 30
3.2 | Obtain the Data | Data Set | Ben Ho | 2022-12-01 | 2022-12-05 | 4 | 0% | bar: WEEK 1 1 to WEEK 2 5
3.3 | Define Scope (ML / AL / DA) & Alogirthms | Scope & Algorithm | Ben Ho | 2022-12-06 | 2022-12-07 | 1 | 0% | bar: WEEK 2 6 to WEEK 2 7
3.4 | Model Building & PoC | Model / Prototype | Ben Ho | 2022-12-08 | 2022-12-15 | 7 | 0% | bar: WEEK 2 8 to WEEK 3 15
3.5 | Result Consolidation | Modelling Result | Ben Ho | 2022-12-16 | 2022-12-18 | 2 | 0% | bar: WEEK 3 16 to WEEK 4 18
4 | Report Compilation
4.1 | Initial Report Draft | Report First Draft | Ben Ho | 2022-12-19 | 2022-12-23 | 4 | 0% | bar: WEEK 4 19 to WEEK 4 23
4.2 | Report Review | Report Review Notes | Ben Ho | 2022-12-24 | 2022-12-25 | 1 | 0% | bar: WEEK 4 24 to WEEK 5 25
4.3 | Final Report Comilation | Final Report | Ben Ho | 2022-12-26 | 2022-12-31 | 5 | 0% | bar: WEEK 5 26 to WEEK 5 31